## November
2014-11-18 | Done yesterday? | Problems/Challenges? | Objective today? | TO-DO
Tobi |  | none | krank
Robert |  | none | Logo research
Daniel |  | none | Tool Shading
Amon |  | none | Level Obstacle 2
Toma |  | none | Diary
2014-11-19 | Done yesterday? | Problems/Challenges? | Objective today?
Tobi | krank | none | krank
Robert | Logo research | none | Unity level Design training, 1st LOGO version
Daniel | Tool Shading | none | Prepare and execute Unity level Design training, Zombie pathfinding
Amon | Level Obstacle 2 | none | Floor Texturen x 5, Nitro Pack, Walls reskin, Road blocker model
Toma | Diary | none | Level 1 x3 (tutorials)-scetch; Plan KW 47 - 48; Ziele and Tasks Sheet update; GDD update; Unity level Design training
2014-11-20 | Done yesterday? | Problems/Challenges? | Objective today?
Tobi | krank | none | 3D model Wheelchair Hero
Robert | Unity level Design training, 1st LOGO version | none | 1st and 2nd Logo Version
Daniel | Unity level Design training, Zombie pathfinding | Zombie pathfinding - scripting difficulties | Camera
Amon | Floor Texturen x 5, Nitro Pack, Walls reskin, Road blocker model | none | Export "boxes", wall remodel, additional road blockers
Toma | Level 1 x3 (tutorials)-scetch; Plan KW 47 - 48; Ziele and Tasks Sheet update; GDD update; Unity level Design training | none | GDD - Target market, difficulty level, Level 1
2014-11-21 | Done yesterday? | Problems/Challenges? | Objective today?
Tobi | 3d model blockout | Proportions | character proportions
Robert
Daniel
Amon
Toma
2014-11-24 | Done yesterday? | Problems/Challenges? | Objective today?
Tobi | character proportions | proportions | character proportions
Robert
Daniel
Amon
Toma
2014-11-25 | Done yesterday? | Problems/Challenges? | Objective today?
Tobi | character proportions | none | retopology
Robert
Daniel
Amon
Toma
2014-11-26 | Done yesterday? | Problems/Challenges? | Objective today?
Tobi | retopology
Robert
Daniel
Amon
Toma
2014-11-27 | Done yesterday? | Problems/Challenges? | Objective today?
Tobi
Robert
Daniel
Amon
Toma
2014-11-28 | Done yesterday? | Problems/Challenges? | Objective today?
Tobi
Robert
Daniel
Amon
Toma

## Dezember
2014-12-01 | Done yesterday? | Problems/Challenges? | Objective today?
Tobi
Robert
Daniel
Amon
Toma |  | Diary | none
2014-12-02 | Done yesterday? | Problems/Challenges? | Objective today?
Tobi
Robert
Daniel
Amon
Toma
2014-12-03 | Done yesterday? | Problems/Challenges? | Objective today?
Tobi
Robert
Daniel
Amon
Toma
2014-12-04 | Done yesterday? | Problems/Challenges? | Objective today?
Tobi
Robert
Daniel
Amon
Toma
2014-12-05 | Done yesterday? | Problems/Challenges? | Objective today?
Tobi
Robert
Daniel
Amon
Toma
2014-12-08 | Done yesterday? | Problems/Challenges? | Objective today?
Tobi
Robert
Daniel
Amon
Toma
2014-12-09 | Done yesterday? | Problems/Challenges? | Objective today?
Tobi
Robert
Daniel
Amon
Toma
2014-12-10 | Done yesterday? | Problems/Challenges? | Objective today?
Tobi
Robert
Daniel
Amon
Toma
2014-12-11 | Done yesterday? | Problems/Challenges? | Objective today?
Tobi
Robert
Daniel
Amon
Toma
2014-12-12 | Done yesterday? | Problems/Challenges? | Objective today?
Tobi
Robert
Daniel
Amon
Toma
2014-12-15 | Done yesterday? | Problems/Challenges? | Objective today?
Tobi
Robert
Daniel
Amon
Toma
2014-12-16 | Done yesterday? | Problems/Challenges? | Objective today?
Tobi
Robert
Daniel
Amon
Toma
2014-12-17 | Done yesterday? | Problems/Challenges? | Objective today?
Tobi
Robert
Daniel
Amon
Toma
2014-12-18 | Done yesterday? | Problems/Challenges? | Objective today?
Tobi
Robert
Daniel
Amon
Toma