## Ziele
Kategorie | Ziele | Tasks | Priority | Done? | Mensch | Zeit(Tage) | User Story
Feature | Hero | 3D model erstellen | A | NO | Tobi | 5 | As player I can navigate the Hero with the arrowkeys in direction left, right, up and down
Feature | Hero | players controls implementieren | A | YES | Daniel | 1
Feature | Hero | animieren | A | NO | Tobi | 3
Feature | Zombie 1 | Movement Script programieren | A | NO | Daniel | 1 | As player I can see that there are Zombie opponents moving on the level so that I can avoid them
Feature | Zombie 1 | 3D Model erstellen | A | NO | Tobi | 3
Feature | Zombie 1 | animieren | A | NO | Tobi | 2
Feature | Zombie 1 | Game Over trigger implementieren | A | YES | Daniel | 1
Modi | Game Modi A | Special Item 3D Model erstellen Medikit | A | YES | Amon | 1 | As player I have to collect N-special Items in order to activate the level exit
Modi | Game Modi A | Special Item 3D Model erstellen Medikit - Redone | A | NO | Amon | 1
Modi | Game Modi A | Special Item 3D Model erstellen Shoping Bag | A | NO | Amon | 1
Modi | Game Modi A | Level Exit 3D Model erstellen | A | YES | Amon | 1
Modi | Game Modi A | Script for collect item condition schreiben | A | YES | Daniel | 1
Modi | Game Modi A | Script for exit level activated schreiben | A | YES | Daniel | 1
Content_Env. | Env. Obstacle 1 (Brick wall_1) | 3D Model erstellen | A | YES | Amon | 1 | As player I can see that the level is made out of a brick wall mace and neither I nor the zombie oppponents can move through the walls
Content_Env. | Env. Obstacle 1 (Brick wall_1) | in Engine importieren | A | YES | Daniel | 1
Feature | Main Menu | Design erstellen | A | NO | Amon | 2 | As a player I can see a menu screen when I open the game and I can click start game button
Feature | Main Menu | in Engine implementieren | A | NO | Daniel | 1
Feature | GUI | Design erstellen | A | NO | ? | 2
Feature | GUI | in Engine implementieren | A | NO | Daniel | 1
Feature | Intro Loading Screen | Design erstellen | A | NO | Amon | 2
Feature | Intro Loading Screen | Text schreiben | A | NO | Toma | 1
Feature | Intro Loading Screen | in Engine importieren | A | NO | Daniel | 1
Feature | Power Up 1 Nitro Pack | 3D Model erstellen | A | NO | Amon | 1 | As a player I can see on some lovels a nitro pack power up placed and when I move over it I see that the speed of the hero is increased by N for N seconds
Feature | Power Up 1 Nitro Pack | in Engine implementieren | A | NO | Daniel | 1
Feature | Power Up 1 Nitro Pack | balansieren | A | NO | Toma | 1
Feature | Power Up 2 Gun | 3D Model erstellen | A | NO | Amon | 1 | As a player I can see on some lovels a gun power up placed and when I move over it I can trigger one shot by pressing the space bar butto which shoots out a projectile that can eliminate one Zombie oponent if it hits it
Feature | Power Up 2 Gun | in Engine implementieren | A | NO | Daniel | 1
Feature | Power Up 2 Gun | balansieren | A | NO | Robert | 1
LEVEL | Level 1 | Level Design erstellen | A | NO | Toma | 1
LEVEL | Level 1 | balansieren | A | NO | Toma | 1
LEVEL | Level 2 | Level Design erstellen | A | NO | Robert | 1
LEVEL | Level 2 | balansieren | A | NO | Robert | 1
Content_item | Medic-kit | 3D Model erstellen | A | YES | Amon | 1 | As a player I have an item that I know i need to colect and I can see it on the level map so that I can colect it and activate the level exit
Content_item | Medic-kit | in Engine implementieren | A | YES | Daniel | 1
Content_item | Oxigen Bar | 3D Model erstellen | A | YES | Amon | 1 | As a player I can see how full my oxygen bar is so that I can estimate how long can I move without taking oxigen packs, I know that the game is over my Oxygen bar gets completely depleted
Content_item | Oxigen Bar | in Engine implementieren | A | YES | Daniel | 1
Content_item | Oxigen Pack | 3D Model erstellen | A | YES | Amon | 1 | As a player I can collect Oxigen Packs placed all over the level map so that I can compansate for the oxygen lost when moving through a virus cloud
Content_item | Oxigen Pack | in Engine implementieren | A | YES | Daniel | 1
Feature | Level Exit | 3D Model erstellen | A | YES | Amon | 1 | As a player I can move to the exit level and if the level victoy condition is acheived I pass the level succesfully
Feature | Level Exit | in Engine implementieren | A | YES | Daniel | 1
Feature | Z-Virus.Cloud | 3D Model erstellen | A | NO | Amon | 1 | As a player I can see that the level is covered almost completely (+ - 80%) by a virus cloud and whenever I am moving through such a field my Oxygen Bar is decreasing
Feature | Z-Virus.Cloud | in Engine implementieren | A | YES | Daniel | 1
Content_NPC | Zombie 2 | Movement Script programieren | B | NO | Daniel | 1 | As game designer I can have a second type of Zombie with different apearance and movement script, which I can place on the levels in order to increase variaty
Content_NPC | Zombie 2 | 3D Model erstellen | B | NO | Tobi | 3
Content_NPC | Zombie 2 | animieren | B | NO | Tobi | 2
Content_NPC | Zombie 2 | Game Over trigger implementieren | B | YES | Daniel | 1
LEVEL | Level 3 | Level Design erstellen | B | NO | Robert | 1
LEVEL | Level 3 | balansieren | B | NO | Robert | 1
LEVEL | Level 4 | Level Design erstellen | B | NO | Robert | 1
LEVEL | Level 4 | balansieren | B | NO | Robert | 1
LEVEL | Level 5 | Level Design erstellen | B | NO | Robert | 1
LEVEL | Level 5 | balansieren | B | NO | Robert | 1
LEVEL | Level 6 | Level Design erstellen | B | NO | Toma | 1
LEVEL | Level 6 | balansieren | B | NO | Toma | 1
LEVEL | Level 7 | Level Design erstellen | B | NO | Toma | 1
LEVEL | Level 7 | balansieren | B | NO | Toma | 1
Modi | Game Modi B | Trapped Survivor 3D Model erstellen | A | NO | Tobi | 1 | Save the trapped survivor
Modi | Game Modi B | Trapped Survivor animieren | A | NO | Tobi | 1
Modi | Game Modi B | Script for level condition schreiben | A | NO | Daniel | 1
Content_Env. | Env. Obstacle 2 (Box) | 3D Model erstellen | A | NO | Amon | 1 | As player I can see that in the level there are boxes placed and neither I nor the zombie oppponents can move through them
Content_Env. | Env. Obstacle 2 (Box) | in Engine importieren | A | NO | Daniel | 1
Content_Env. | Env. Obstacle 3 (...) | 3D Model erstellen | A | NO | Amon | 1 | As player I can see that in the level there are …. placed and neither I nor the zombie oppponents can move through them
Content_Env. | Env. Obstacle 3 (...) | in Engine importieren | A | NO | Daniel | 1
Content_Env. | Env. Obstacle 4 (...) | 3D Model erstellen | B | NO | Amon | 1 | As player I can see that in the level there are …. placed and neither I nor the zombie oppponents can move through them
Content_Env. | Env. Obstacle 4 (...) | in Engine importieren | B | NO | Daniel | 1
Content_Env. | Env. Obstacle 5 (...) | 3D Model erstellen | B | NO | Amon | 1 | As player I can see that in the level there are …. placed and neither I nor the zombie oppponents can move through them
Content_Env. | Env. Obstacle 5 (...) | in Engine importieren | B | NO | Daniel | 1
Content_Env. | Env. Obstacle 6 (...) | 3D Model erstellen | B | NO | Amon | 1 | As player I can see that in the level there are …. placed and neither I nor the zombie oppponents can move through them
Content_Env. | Env. Obstacle 6 (...) | in Engine importieren | B | NO | Daniel | 1
Content_Env. | Level Floor 1 (...) | 3D Model erstellen | A | NO | Amon | 1
Content_Env. | Level Floor 1 (...) | in Engine importieren | A | NO | Daniel | 1
Content_Env. | Level Floor 2 (...) | Model erstellen | A | NO | Amon | 1
Content_Env. | Level Floor 2 (...) | in Engine importieren | A | NO | Daniel | 1
Content_Env. | Level Floor 3 (...) | Model erstellen | B | NO | Amon | 1
Content_Env. | Level Floor 3 (...) | in Engine importieren | B | NO | Daniel | 1
Content_Env. | Level Floor 4 (...) | Model erstellen | B | NO | Amon | 1
Content_Env. | Level Floor 4 (...) | in Engine importieren | B | NO | Daniel | 1
Modi | Game Modi C | Script for level condition schreiben | A | NO | Daniel | 1 | Zombie opponents are entereing the lavel in N time intervals and the objective is simply to find the way out
Feature | Power Up 3 Flamethrower | 3D Model erstellen | A | NO | Amon | 1 | the flamethrower, when collected by the player gives N soconds of invulnarability against Zombies and when the player colides with Zombies, they are eliminated
Feature | Power Up 3 Flamethrower | in Engine implementieren | A | NO | Daniel | 1
Feature | Power Up 3 Flamethrower | balansieren | A | NO | Robert | 1
Feature | Save Game Option | Script | C | NO | Daniel | 1
Feature | Point system | in Engine implementieren | C | NO | Daniel
Feature | Point system | balansieren | C | NO | Toma
Feature | High Score | in Engine implementieren | C | NO | Daniel
Sound | Sound - Menu, Zwischen Screen | komponieren und erstellen | B | NO
Sound | Sound - Level | komponieren und erstellen | B | NO
Sound | Sounds implementieren | in Engine implementieren | B | NO | Daniel
Sound | Sound(s) - Hero | erstellen | B | NO
Sound | Sound(s) - Zombie | erstellen | B | NO
Sound | Sound(s) - Power Ups | erstellen | B | NO
Sound | Sound - Game Over | erstellen | B | NO
Sound | Sound - Victory! | erstellen | B | NO
Sound | Sound - Click Menu | erstellen | B | NO
Sound | Sound - Objective Colected | erstellen | B | NO
Sound | Sound(s) - Items | erstellen | B | NO
Content Menu | Zwischen Screens | texts schreiben | C | NO | Amon, Tobi
Content Menu | Zwischen Screens | Bilder hinzufügen | C | NO | Robert, Toma
Content Menu | Zwischen Screens | in Engine implementieren | C | NO | Daniel
Design | Game Logo | Game Logo erstellen | A | NO | Robert
Content Menu | Level Map overview | Map Zeichnen | B | NO | Amon, Toma |  | As a player I have an overview on my progress throughout the levels
Content Menu | Level Map overview | in Engine implementieren | B | NO | Daniel

## Zeitplan
Phasen | Konzeption | Pre-Production |  |  | Production | [5 empty] | Alpha-Milestone |  |  | Beta-Milestone
| Past | Past | Pitch | Past | Past |  |  | Milestone 01 |  |  |  |  | Milestone 02 |  |  | Goldmaster
Datum Freitag |  |  | 2014-11-14 | 2014-11-21 | 2014-11-28 | 2014-12-05 | 2014-12-12 | 2014-12-19 | 2014-12-26 | 2015-01-02 | 2015-01-09 | 2015-01-16 | 2015-01-23 | 2015-01-30 | 2015-02-06 | 2015-02-13
KW | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 1 | 2 | 3 | 4 | 5 | 6 | 7
Ziele: | Boot camp | High konzept | Pitch-Präsi | Hero/ 3D model | Hero/animieren | Trapped Survivor | Game Modi D | GUI | Holiday |  | Level Design | Level Polish |  | Grafik Polish | BLOCK
| Game Vision | Art and Game reference | Pitch-Doc | Level 2 | Game Modi B | Level 3 | Level 4 | Asset -Redesign |  |  | Assets setting 1 | Assets setting 1 |  | Testing | > no more features
| Team Building | Core feature definition | GDD (ongoing) | Level 1 x3 (Tutorials) | Zombie1 / 3D model | Zombie 3 | Level 5 | menu | Box feature |  | Assets setting 2 | Assets setting 2 |  | Balance | > only polish, test, balance
|  |  | Prototype Game Modi A | Menu | Zwischen Screen | Power Up 3 | Setting 1 assets | FOW | Assets for 2 settings |  | player feedabck polish | Level Map |  | Final Content input
|  |  |  | Power Up 1 Nitro Pack |  | Zombie1/animieren | Setting 2 assets | player Feedback | Level Design x 4 |  | Trapped Survivor x2 | power up 4&5
|  |  |  | Z-Virus.Cloud | Kamera | GUI | Power Up 2 Gun | Sound Import | Zombie 2 |  | GUI poslish
|  |  |  | Env. Obstacle 2 | Assets Wohnzimmer | Assets SuperMarkt | Menu | Tutorial level | power up 2&3 |  | Sound 2 import
|  |  |  | Env. Obstacle 3 | Hero/ 3D model | Texturen SuperMarkt | Zwischen Screen | level x1 | Trapped Survivor x2 |  | power up 2&3
|  |  |  | Logo | Texturen Wohnzimmer | Zombie 2 |  | Hero Redesign
[6 empty] | Game Modi C |  | LOGO - redesign
Model Shoping Bag
Level 1 x3 (Tutorials)
Level 2