## Tabelle1
| Note | $ | Imp. | Priority | Mensch |  | $ | Imp.
Gameplay | [5 empty] | A | low | High
Steuerung | [5 empty] | B | High | High
GUI - Health Bar | [5 empty] | C | low | low
power up 1 | [5 empty] | D | High | low
NPC 1
Sound
Musik
Effekte
Voice Over(?)
Feedback
GUI - Player input FB
GUI - collect FB
Game Over
Objectives - Navigation
Virus Cloud FB
Vignett - polish
Graphik
Animation PC
Animation NPC
Farbigkeit
Level Design
Levelcount (?)
Tutorial
Setting 2
Menu & Intro
Credits
Dokumentation
Vision Document
GDD
Presentation
Packaging

## Tabelle2
Bereich | Aufgabe | Priorität | Status | Mensch | Komentar | sound?
Documentation | GDD | A |  | Robert | in word
Documentation | GDD | A |  | Toma
Documentation | Task check | A |  | Toma | ongoing
Feedback | Antidot | A |  | Daniel | collect effekt "Puff!" partikel effekt
Feedback | Antidot | A |  | Daniel | collect effekt "Puff!" sound
Feedback | left_right | A |  | Daniel | Blinker_Script
Feedback | left_right | A |  | Tobi | Blinker_Textur
Feedback | game over | A |  | Andi | game over box design
Feedback | game over | A |  | Daniel | Script
Feedback | game success | A |  | Andi | game success box design
Feedback | game success | A |  | Daniel | Script
Feedback | hit wall | A |  | Daniel | Script & Sound | sound
Feedback | Z-Virus | A |  | Andi | Box pop up
Feedback | Z-Virus | A |  | Daniel | Box pop up | sound
Feedback | Vignett | A |  | Daniel | pulsieren
Feedback | Vignett | A |  | Daniel | Script & Sound (husten) | sound
Feedback | Comic Cloud | B |  | Andi | transform Zombie in TS during S.A.Antidot
Feedback | Hero Animations | A |  | Tobi | Hero aniations, avoid stale effekt | sound
Gameplay | Steuerung | A |  | Daniel | Sanftere Übergänge (?)
Gameplay | Kolision | A |  | Daniel | Zombie Kolision optimieren | sound ?
GUI | Healthbar | A |  | Andi | Design 1
GUI | Healthbar | A |  | Amon | Design 2 | sound
GUI | Level objective | A |  | Andi | Design 1
GUI | Level objective | A |  | Amon | Design 2
GUI | Minimap | A |  | Daniel | optimize, center
GUI | Zielanzeiger | A |  | Daniel | Script
GUI | Zielanzeiger | A |  | Andi | Design 1
GUI | Zielanzeiger | A |  | Amon | Design 2
GUI | Briefing Box | A |  | Daniel | Script
GUI | Briefing Box | A |  | Andi | Design 1
GUI | Briefing Box | A |  | Amon | Design 2 incl.Collectable Icon
GUI | Game Over | A |  | Tobi | Sad Hero (only Face)
GUI | game success | A |  | Tobi | happy Hero (only Face)
GUI | TS icon | A |  | Tobi | Kopf der verschiedenen TSs als Icon in GUI
Item | Alarm | A |  | Amon | Design x2 Items (alarm with effekt, trigger)
Item | Alarm | A |  | Daniel | Script
Item | Alarm | A |  | Daniel | Sound | sound
Item | S.A.Antidot | A |  | Amon | Design
Item | S.A.Antidot | A |  | Daniel | Script (trigger, effekt, zombie pathfind.,hero, zombie turn)
Item | S.A.Antidot | A |  | Daniel | Sound | sound
Level Design | Level re-do | A |  | Robert
Level Design | Level re-do | A |  | Toma | Tutorial
Level Design | Level | A |  | Toma
Level Design | Level | A |  | Toma
Level Design | Level | B |  | Toma
Level Design | Level | A |  | Robert |  | sound
Level Design | Level | A |  | Robert
Level Design | Level | B |  | Robert
Menu | intro | A |  | Daniel | GA Logo and stuff
Menu | main menu | A |  | Daniel | play, load level, credits, Exit | sound
Menu | esc. = Exit | A |  | Daniel | in game escape
Menu | choose level | A |  | Daniel | unlock and choose level
Menu | box | A |  | Andi | Text box
Menu | animation | B |  | Tobi | zombie chase hero, animation for the main menu
NPC | TS_Hund | A |  | Tobi | Model, Animation, Textur
NPC | TS_Hund | B |  | Daniel | Script & Sound
NPC | TS_Katze | B |  | Tobi | Model, Animation, Textur
NPC | TS_Katze | B |  | Daniel | Script
NPC | TS_Oma | A |  | Tobi | Model, Animation, Textur
NPC | TS_Oma | B |  | Daniel | Script
NPC | TS_Man | B |  | Tobi | Model, Animation, Textur
NPC | TS_Man | B |  | Daniel | Script & Sound
NPC | TS_Frau | B |  | Tobi | Model, Animation, Textur
NPC | TS_Frau | B |  | Daniel | Script & Sound
NPC | Zombie_2 | A |  | Tobi | Model, Animation, Textur
NPC | Zombie_2 | B |  | Daniel | Script & Sound
NPC | Zombie_2 | B |  | Daniel | Script Chase Screen Shake & Sound | sound
Setting | Boden | A |  | Amon | Design
Setting | Boden | A |  | Andi | Design
Setting | slow_Boden | A |  | Amon | Design
Setting | slow_Boden | A |  | Andi | Design
Setting | slow_Boden | A |  | Daniel | Script
Setting | Farbensättigung | A |  | Amon | Farben hochdrehen
Setting | unic lvl assets | A |  | Andi
Setting | unic lvl assets | A |  | Amon
Level Design | Tutorial | A |  | Daniel | Tutorial Level Polish with Toma
Documentation | Presentation | A |  | Toma
Documentation | Daniel Feedback Meeting | A |  | Toma | prepare meeting with Daniel - goal reduction
Documentation | Logbuch | A |  | Toma
Gameplay | Sound Check | A |  | Toma | document and communicate sound and SFX list (with team and Markus)